## 0405
Date: | 2021-05-04
Attendees: | All
Action Review
Action: | Progress:
Wenda building server | Working on integration with front end
Stanni designing globe | Stopping work on this as we are going with threejs
Start writing documentation | Emily, Hamza, Jess have started - Jess has updated GitHub
Final evaulation: have a new group, similar but more formal procedure | Not started yet
Create affinity diagramming | Not started yet
Start translating documentation to md files | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Documentation | All | End of next week
HCI Evaluation/Thematic analysis | All | End of next week
Figure out front and back end relation!!! | Hamza, Wenda, Jess | Tomorrow
Decisions
Useful Links
Purpose: | Link:

## 0505
Date: | 2021-05-04
Attendees: | All
Action Review
Action: | Progress:
Start writing documentation | Emily, Hamza, Jess, Stanni have started - Jess has updated GitHub
Final evaulation: have a new group, similar but more formal procedure | Not started yet
Create affinity diagramming | Not started yet
HCI Evaluation/Thematic analysis | Wenda and Stanni to look at
Figure out front and back end relation!!! | Completed (met with Marceli - all on track)
New Actions and Owners
Action: | Owner: | Date of completion:
Transcribe feedback sessions | Jess | Tomorrow
Create seeding script | Jess | Tomorrow
Thematic analysis of feedback | Stanni & Wenda | End of this week
Deploy website | All | End of this week
Decisions
If we have enough time next week (after writing documentation) we will integrate POST functions
Useful Links
Purpose: | Link: