## 0604
Date: | 2021-04-06
Attendees: | Hamza, Emily, Stanni, Jess
Action Review
Action: | Progress:
New Actions and Owners
Action: | Owner: | Date of completion:
Go through angular workshops | Hamza
Go through express workshops | Jess
Finalise prototypes | Emily
Decisions
Looking at feedback - like idea of stars and space ships in the background (behind the globe)
Thinking about using a gradient of colours instead of brightness of light to illustrate literacy rates
Useful Links
Purpose: | Link:

## 0704
Date: | 2021-04-07
Attendees: | All
Action Review
Action: | Progress:
Hamza crash course HTML | Completed
Emily prototype | Added sound, background, moving moon
Jess going through workshops | Completed, needs debugging
New Actions and Owners
Action: | Owner: | Date of completion:
Typescript crash course | Hamza | Tomorrow
Prototype developing sound | Emily | Tomorrow
Learning about how to design globe | Stanni | This week
Debug test site, connect our own data to the charts currently up | Jess | Tomorrow
Building server | Wenda | This week
Decisions
Useful Links
Purpose: | Link:

## 0804
Date: | 2021-04-08
Attendees: | All
Action Review
Action: | Progress:
Hamza typescript crash course | On track
Emily prototype | Created colour blocked version
Jess going through workshops | Completed and debugged
Wenda building server | Working on it
Stanni designing globe | Working on it
New Actions and Owners
Action: | Owner: | Date of completion:
Connect database to charts | Wenda and Jess | This week(end)
Get data from CSV file into database | Jess (with advice from Stanni) | This week(end)
Feedback sessions | All | Sunday
Prototype with fluorescent colours, darker ocean | Emily | This week(end)
Decisions
Emily to help Wenda and Jess get back end off the ground if necessary
Useful Links
Purpose: | Link:
TypeScript crash course | https://www.youtube.com/watch?v=k5E2AVpwsko&t=2086s&ab_channel=ProgrammingwithMosh
Import data into Mongo official docs | https://docs.mongodb.com/guides/server/import/
How to import a CSV into MongoDB | https://kb.objectrocket.com/mongo-db/how-to-import-a-csv-into-mongodb-327

## 1204
Date: | 2021-04-12
Attendees: | All
Action Review
Action: | Progress:
Hamza typescript crash course | On track
Connect database to charts | Working on it - encountered problems
Feedback sessions | Ongoing
Get data from CSV file into database | Same as above
Wenda building server | Working on it
Stanni designing globe | Working on it
Prototype with fluorescent colours, darker ocean | Ongoing
New Actions and Owners
Action: | Owner: | Date of completion:
Find out how to import data into mongo outside of Docker | Jess | Tomorrow
Decisions
Useful Links
Purpose: | Link:

## 1604
Date: | 2021-04-16
Attendees: | All
Action Review
Action: | Progress:
Hamza typescript crash course | Completed
Connect database to charts | Working on it - encountered problems
Feedback sessions | Completed this round
Get data from CSV file into database | Completed
Wenda building server | Working on it
Stanni designing globe | Working on it
Prototype with fluorescent colours, darker ocean | Ongoing
Find out how to import data into mongo outside of Docker | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Look into rotating the globe | Stannni | This week
Link up coordinates of each country to code | Stanni and Hamza | This week
Investigate whether we need a router to link up different pages | All | This week
Decisions
Hamza to review and neaten report, everyone to volunteer for own sections
Useful Links
Purpose: | Link:
API design | https://launchany.com/resolving-the-frontendbackend-api-design-conflict/

## 1904
Date: | 2021-04-19
Attendees: | All
Action Review
Action: | Progress:
Connect database to charts | Routing database display modules completed, able to access database from api and display data in response
Wenda building server | Working on it - working on GET functions in server
Stanni designing globe | Working on it - working on tool tips and movements
Prototype with fluorescent colours, darker ocean | Completed
Look into rotating the globe | Working on it - Hamza able to do so in 3js through moving the camera, more difficult in d3
Link up coordinates of each country to code | Working on it - might take longer to complete than expected
Investigate whether we need a router to link up different pages | All | This week
New Actions and Owners
Action: | Owner: | Date of completion:
Front end targets for this week: working on textures, lag, light in globe | Hamza | End of week
Front end targets for this week: working on movement, tool tips, extra: colours | Stanni | End of week
Back end targets: improvement in GET functions and building the server | Wenda (Emily to support) | End of week
Back end targets: help Wenda to swap out json file for accessing the database | Jess (Emily to support) | End of week
Design targets: replace feedback sessions with globe instead of prototype | All (Emily to lead) | End of week
Design targets: start writing documentation initial sketches | All | End of week
Decisions
Jess (and Hamza if needed) to help with SCRUM responsibilities
Useful Links
Purpose: | Link:
API design | https://launchany.com/resolving-the-frontendbackend-api-design-conflict/

## 2204
Date: | 2021-04-22
Attendees: | All
Action Review
Action: | Progress:
Wenda building server | Working on it - working on GET functions in server
Stanni designing globe | Working on it - working on tool tips and movements
Look into rotating the globe | Working on it - Hamza able to do so in 3js through moving the camera, more difficult in d3
Link up coordinates of each country to code | Working on it - might take longer to complete than expected
Investigate whether we need a router to link up different pages | Completed - should be ok as is
New Actions and Owners
Action: | Owner: | Date of completion:
Decisions
Review with Marceli - all on track in his opinion
Useful Links
Purpose: | Link:

## 2304
Date: | 2021-04-23
Attendees: | All
Action Review
Action: | Progress:
Wenda building server | Working on it - completed GET functions, need to test (problems with Docker)
Stanni designing globe | Working on it - working on tool tips and movements (problems with integrating with Angular)
Look into rotating the globe | Completed
Link up coordinates of each country to code | Completed
Investigate whether we need a router to link up different pages | Completed - should be ok as is
Front end targets for this week: working on textures, lag, light in globe | Completed
Front end targets for this week: working on movement, tool tips, extra: colours | Progress made, problems with linking d3 and Angular
Back end targets: improvement in GET functions and building the server | Progress made, Wenda having problems with Docker making it hard to test - Jess has built some database query functions, need to alter to return value instead of just printing)
Back end targets: help Wenda to swap out json file for accessing the database | Completed (needs testing)
Design targets: replace feedback sessions with globe instead of prototype | Ongoing
Design targets: start writing documentation initial sketches | Progress made - created "working plan" document for everyone to work on their sections in
New Actions and Owners
Action: | Owner: | Date of completion:
Front end targets: display data on website and make it look nice, then add slider in later | Hamza | Next week
Front end targets: connecting front end and back end, looking at timeline, tool tips | Stanni | Next week
Back end targets: connecting front and back end, think about slider | Wenda | Next week
Back end targets: check database volumes are correct on each branch, get functions returning data instead of just printing to the console | Jess | Next week
Design targets: start testing, help with other tasks, learn a bit of HTML and CSS | Emily to lead | Next week
Useful Links
Purpose: | Link:

## 2604
Date: | 2021-04-26
Attendees: | All
Action Review
Action: | Progress:
Wenda building server | Working on it - need to integrate with front end
Stanni designing globe | Working on it - difficult bugs to fix encountered linking d3 and Angular
Design targets: replace feedback sessions with globe instead of prototype | Ongoing
New Actions and Owners
Action: | Owner: | Date of completion:
Start writing documentation | All | This week
Routing: perhaps have a separate page for book animation | Wenda/Stanni/Hamza | Deadline
Combine data and coordinate collections | Jess | This week
Start testing | Emily | This week
Document framework/methodology for feedback | Hamza | This week
Test Wenda's functions and let him know if there are errors | Jess | This week
Decisions
Useful Links
Purpose: | Link:

## 2904
Date: | 2021-04-29
Attendees: | All
Action Review
Action: | Progress:
Wenda building server | Working on it - need to integrate with front end
Stanni designing globe | Working on it - connected d3 with Angular
Design targets: replace feedback sessions with globe instead of prototype | Ongoing
Start writing documentation | Ongoing
Routing: perhaps have a separate page for book animation | Ongoing (lower priority)
Combine data and coordinate collections | Completed
Start testing | Framework written
Document framework/methodology for feedback | Ongoing
Test Wenda's functions and let him know if there are errors | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Meet tomorrow to connect front and back end | Jess, Hamza, Wenda | Tomorrow (30th)
Final evaulation: have a new group, similar but more formal procedure | All | End of next week
Create affinity diagramming | Hamza/Emily/Jess | End of next week
Decisions
Focus group is actually more of a codesign group - user driven process
Useful Links
Purpose: | Link: