## 0604
Date: | 2021-04-06
Attendees: | Hamza, Emily, Stanni, Jess
Action Review
Action: | Progress:
New Actions and Owners
Action: | Owner: | Date of completion:
Go through angular workshops | Hamza
Go through express workshops | Jess
Finalise prototypes | Emily
Decisions
Looking at feedback - like idea of stars and space ships in the background (behind the globe)
Thinking about using a gradient of colours instead of brightness of light to illustrate literacy rates
Useful Links
Purpose: | Link:

## 0704
Date: | 2021-04-06
Attendees: | Hamza, Emily, Stanni, Jess
Action Review
Action: | Progress:
Hamza crash course HTML | Completed
Emily prototype | Added sound, background, moving moon
Jess going through workshops | Completed, needs debugging
New Actions and Owners
Action: | Owner: | Date of completion:
Typescript crash course | Hamza | Tomorrow
Prototype developing sound | Emily | Tomorrow
Learning about how to design globe | Stanni | This week
Debug test site, connect our own data to the charts currently up | Jess | Tomorrow
Building server | Wenda | This week
Decisions
Useful Links
Purpose: | Link: