## Group Project Tracker
EASTER BREAK
Task | Owner | Status | w/c 22 Mar | w/c 29 Mar | w/c 5 Apr | w/c 12 Apr | w/c 19 Apr | w/c 26 Apr | w/c 3 May | Submission Date: 7 May
Write report (readme.md file) | All (Emily/Hamza) | Pending
Team | All - provide image and bio of themselves | Pending
Introduction | All - begun by Jess | Pending
Background and Motivation | Emily | Pending
System Implementation | All (on area of Ownership) | Pending
UX Design | Hamza/Stanni? | Pending
Sprints & Project Management | Emily/Hamza | Pending
Evaluation | Emily/Hamza | Pending
Conclusion | Emily/Hamza | Pending
Team Organisation | All | Completed
Set up github repository | Jess | Completed
Skills mapping | Hamza | Completed
Formalise roles using RASCI | Hamza | Completed
Ideation | All | Pending
Brainstorming and mashup | All | Completed
Incorporate ideas from feedback session | All | Pending
Design | All | Pending
Competitor analysis | TBD | Pending
Produce wireframe | Hamza/Emily | Pending
Scoping project | All | Completed
Design paper prototypes | Hamza | Completed
Evaluation and Results | All | Pending
Understanding Problem Space | All | Pending
Ethical analysis | TBD | Pending
Stakeholder Analysis | Jess | Completed
Background research into serious topic | Jess | Completed
Primary Research | All | Pending
Establish hypotheses | Emily | Pending
Define research questions | Emily | Pending
Create and share survey | All | Completed
Analysis of survey results | Emily | Pending
Establish and maintain focus group | TBD | Pending
User observation | TBD | Pending
Pilot Testing | TBD | Pending
Technical Implementation | All | Pending
Develop MEAN stack skills/familiarity | All | Pending
Triangulate data sources |  | Pending
Database | Jess | Pending
Clean/prepare data |  | Pending
Finalise data model | Jess | Pending
Back-end | All (Wenda) | Pending
RESTful API |  | Pending
Deploying with Docker - runtime environment |  | Pending
Front-end | Stanni | Pending
Pending
UI/UX | Hamza | Pending
Pending
Testing | All (Emily) | Pending
Unit Testing |  | Pending
Integration Testing |  | Pending
Quality Assurance | Emily | Pending
Pending