## Sheet1
Date: | 2021-05-04
Attendees: | All
Action Review
Action: | Progress:
Wenda building server | Working on integration with front end
Stanni designing globe | Stopping work on this as we are going with threejs
Start writing documentation | Emily, Hamza, Jess have started - Jess has updated GitHub
Final evaulation: have a new group, similar but more formal procedure | Not started yet
Create affinity diagramming | Not started yet
Start translating documentation to md files | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Documentation | All | End of next week
HCI Evaluation/Thematic analysis | All | End of next week
Figure out front and back end relation!!! | Hamza, Wenda, Jess | Tomorrow
Decisions
Useful Links
Purpose: | Link: