## 0604
Date: | 2021-04-06
Attendees: | Hamza, Emily, Stanni, Jess
Action Review
Action: | Progress:
New Actions and Owners
Action: | Owner: | Date of completion:
Go through angular workshops | Hamza
Go through express workshops | Jess
Finalise prototypes | Emily
Decisions
Looking at feedback - like idea of stars and space ships in the background (behind the globe)
Thinking about using a gradient of colours instead of brightness of light to illustrate literacy rates
Useful Links
Purpose: | Link:

## 0704
Date: | 2021-04-07
Attendees: | All
Action Review
Action: | Progress:
Hamza crash course HTML | Completed
Emily prototype | Added sound, background, moving moon
Jess going through workshops | Completed, needs debugging
New Actions and Owners
Action: | Owner: | Date of completion:
Typescript crash course | Hamza | Tomorrow
Prototype developing sound | Emily | Tomorrow
Learning about how to design globe | Stanni | This week
Debug test site, connect our own data to the charts currently up | Jess | Tomorrow
Building server | Wenda | This week
Decisions
Useful Links
Purpose: | Link:

## 0804
Date: | 2021-04-08
Attendees: | All
Action Review
Action: | Progress:
Hamza typescript crash course | On track
Emily prototype | Created colour blocked version
Jess going through workshops | Completed and debugged
Wenda building server | Working on it
Stanni designing globe | Working on it
New Actions and Owners
Action: | Owner: | Date of completion:
Connect database to charts | Wenda and Jess | This week(end)
Get data from CSV file into database | Jess (with advice from Stanni) | This week(end)
Feedback sessions | All | Sunday
Prototype with fluorescent colours, darker ocean | Emily | This week(end)
Decisions
Emily to help Wenda and Jess get back end off the ground if necessary
Useful Links
Purpose: | Link:
TypeScript crash course | https://www.youtube.com/watch?v=k5E2AVpwsko&t=2086s&ab_channel=ProgrammingwithMosh
Import data into Mongo official docs | https://docs.mongodb.com/guides/server/import/
How to import a CSV into MongoDB | https://kb.objectrocket.com/mongo-db/how-to-import-a-csv-into-mongodb-327