## 0405
Date: | 2021-05-04
Attendees: | All
Action Review
Action: | Progress:
Wenda building server | Working on integration with front end
Stanni designing globe | Stopping work on this as we are going with threejs
Start writing documentation | Emily, Hamza, Jess have started - Jess has updated GitHub
Final evaulation: have a new group, similar but more formal procedure | Not started yet
Create affinity diagramming | Not started yet
Start translating documentation to md files | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Documentation | All | End of next week
HCI Evaluation/Thematic analysis | All | End of next week
Figure out front and back end relation!!! | Hamza, Wenda, Jess | Tomorrow
Decisions
Useful Links
Purpose: | Link:

## 0505
Date: | 2021-05-04
Attendees: | All
Action Review
Action: | Progress:
Start writing documentation | Emily, Hamza, Jess, Stanni have started - Jess has updated GitHub
Final evaulation: have a new group, similar but more formal procedure | Not started yet
Create affinity diagramming | Not started yet
HCI Evaluation/Thematic analysis | Wenda and Stanni to look at
Figure out front and back end relation!!! | Completed (met with Marceli - all on track)
New Actions and Owners
Action: | Owner: | Date of completion:
Transcribe feedback sessions | Jess | Tomorrow
Create seeding script | Jess | Tomorrow
Thematic analysis of feedback | Stanni & Wenda | End of this week
Deploy website | All | End of this week
Decisions
If we have enough time next week (after writing documentation) we will integrate POST functions
Useful Links
Purpose: | Link:
SCRUM/Kanban methodology | https://www.atlassian.com/agile/kanban/kanban-vs-scrum
https://www.atlassian.com/agile/kanban#:~:text=Kanban%20is%20a%20popular%20framework,of%20work%20at%20any%20time

## 0705
Date: | 2021-05-07
Attendees: | All
Action Review
Action: | Progress:
Start writing documentation | Everyone started
Final evaulation: have a new group, similar but more formal procedure | Not started yet
Create affinity diagramming | Not started yet
HCI Evaluation/Thematic analysis | Wenda and Stanni have transcripts, working on over the weekend
Transcribe feedback sessions | Completed
Create seeding script | Completed
Deploy website | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Finish documentation | All | Wednesday
Adding instruction box pop up | Hamza | Wednesday
Format info box & put percentage | Hamza | Wednesday
Put in link to the source of the data (contextualise data - explaining what the data is showing - percentage of who?) | Hamza | Wednesday
testing edge cases, adapting functions for edge not core to test functionality in more detail | Emily | Wednesday
make sure we're doing integration testing by pulling data service through globe component by testing outcome | Emily | Wednesday
test the data service to make sure it's giving the right response | Emily | Wednesday
Decisions
If we have enough time next week (after writing documentation) we will integrate POST functions
Useful Links
Purpose: | Link:

## 1105
Date: | 2021-05-11
Attendees: | All
Action Review
Action: | Progress:
Start writing documentation | Everyone started, nearly all sections complete
Final evaulation: have a new group, similar but more formal procedure | One feedback session completed
Create affinity diagramming | Not started yet
HCI Evaluation/Thematic analysis | Wenda completed, Stanni finishing tonight
Adding instruction box pop up | Completed
Format info box & put percentage | Completed
Put in link to the source of the data (contextualise data - explaining what the data is showing - percentage of who?) | Completed
testing edge cases, adapting functions for edge not core to test functionality in more detail | Completed
make sure we're doing integration testing by pulling data service through globe component by testing outcome | Completed
test the data service to make sure it's giving the right response | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Finish documentation | All | Wednesday
Final feedback session | Jess | Tonight
Stanni to help Wenda with documentation if necessary | Stanni | Wednesday
If we have time, lit analysis on serious play | Jess | Wednesday
Final thematic analysis | Wenda, or Stanni | Wednesday
Decisions
MVP done by Wednesday, completely finished by Thursday so that we can format and review hyperlinks
Useful Links
Purpose: | Link: