## 0403
Date: | 2021-03-04
Attendees: | All
Action Review
Action: | Progress:
Paper prototypes | Completed and reviewed
Define team roles | Completed aside from deciding back-end responsibility
New Actions and Owners
Action: | Owner: | Date of completion:
Think about evaluation of paper prototypes | All | Friday (5th March)
Think about why we have chosen literacy rates | All | Friday (5th March)
Decisions
Consider mark scheme and how we are documenting our process | Why are we focussing on literacy rates? | Who are we catering to? | Why are we catering to them specifically? | Why does the website look a certain way? | Why are certain colours used?
Useful Links
Purpose: | Link:
See github repo for paper prototypes | https://github.com/jess-mw/desk23/tree/main/DesignElements
Useful link if we plan on creating our own 3D assets | https://medium.com/@matthewmain/how-to-import-a-3d-blender-object-into-a-three-js-project-as-a-gltf-file-5a67290f65f2
Inspiration for mapping literacy rates, use of colour, hovering over areas for more information | https://worldpopulationreview.com/country-rankings/literacy-rate-by-country
Example project with similar ideas, documentation of process, exploration of data | https://towardsdatascience.com/visualizing-literacy-rate-disparity-19f375486965
Paper prototypes review | https://teams.microsoft.com/l/file/5A7FD25B-AC3B-49AF-93F3-E2F3254B4B63?tenantId=b2e47f30-cd7d-4a4e-a5da-b18cf1a4151b&fileType=docx&objectUrl=https%3A%2F%2Fuob.sharepoint.com%2Fteams%2Fgrp-segp-uob%2FShared%20Documents%2FDesk%2023%2FPaperPrototypesReview.docx&baseUrl=https%3A%2F%2Fuob.sharepoint.com%2Fteams%2Fgrp-segp-uob&serviceName=teams&threadId=19:40cbe17469d8405e95c57fbe40e020da@thread.tacv2&groupId=a9a647c8-66d1-4f10-bd04-9a5ed3f67e7b

## 0503
Date: | 2021-03-05
Attendees: | All
Action Review
Action: | Progress:
Evaluation of paper prototypes | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
No new actions
Decisions
Will wait to decide who is responsible for back end until we understand more about what it entails
Finalised website idea - see Literacy rates ideation phase
Useful Links
Purpose: | Link:

## 0903
Date: | 2021-03-09
Attendees: | All
Action Review
Action: | Progress:
New Actions and Owners
Action: | Owner: | Date of completion:
Create survey monkey | Emily & Hamza | This week
Finalise paper prototypes | Hamza | This week
Create data model | all | This week
Decisions
Spoke to Stuart who advised us that we are on track, and that we should consider a 2D map instead of a globe, which may be more technically feasible. Also that we should keep in mind the existing tools and how our product will be innovative. We are on the serious end of play, but he thought that there was sufficient play to be addressing the brief adequately | To address this, we will create a survey of our prototypes that we will send out to family and friends to elicit responses, which we can use to adjust our design
Useful Links
Purpose: | Link:

## 1103
Date: | 2021-03-11
Attendees: | All
Action Review
Action: | Progress:
Survey monkey | Created basic template, going to add more questions
Finalise prototype | Made, going to add more features
New Actions and Owners
Action: | Owner: | Date of completion:
Finalise prototype | Hamza | Next week
Finalise survey monkey | Emily | Next week
Develop data model | Jess | Next week
Write project outline for github | Jess | Next week
Create header page for website | Stanni | Next Week
Decisions
Asking people what they know about literacy rates to gather an idea of general knowledge/understanding | Extra comments section at the bottom | Ask people what they think of the visual qualities
Uploaded data to teams from https://ourworldindata.org/literacy
Useful Links
Purpose: | Link:

## 1603
Date: | 2021-03-16
Attendees: | All
Action Review
Action: | Progress:
Finalise prototype | Hamza | Finalising
Finalise survey monkey | Emily | Completed
Develop data model | Jess | Basic version completed
Write project outline for github | Jess | Completed
Create header page for website | Stanni | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Share survey with friends and family | All | This week
Create focus group of family and friends that we can keep talking to as our project develops | All | Ongoing
Become more familiar with the mean stack | All | This week
Decisions
Perhaps have the globe coming out of the book?
Wenda to start working on understanding back end
Hamza and Emily focussing on design, Stanni's job to implement it
Useful Links
Purpose: | Link:

## 1703
Date: | 2021-03-17
Attendees: | All
Action Review
Action: | Progress:
Finalise prototype | Hamza | Finalising
Share survey with friends and family | All | Finalising
Create focus group of family and friends that we can keep talking to as our project develops | All | Ongoing
Become more familiar with the mean stack | All | Ongoing
New Actions and Owners
Action: | Owner: | Date of completion:
Complete stakeholder analysis | Jess | This week
Decisions
No new decisions
Useful Links
Purpose: | Link:
See Stakeholder Analysis document and Miro page (on GitHub and Teams)

## 1803
Date: | 2021-03-18
Attendees: | All
Action Review
Action: | Progress:
Finalise prototype | Hamza | Finalising
Share survey with friends and family | All | Finalising
Create focus group of family and friends that we can keep talking to as our project develops | All | Ongoing
Become more familiar with the mean stack | All | Ongoing
Complete stakeholder analysis | Jess | Completed
New Actions and Owners
Action: | Owner: | Date of completion:
Do the Docker workshop | All | This week or next
Decisions
Gone over scoping of project (see document Scoping in Prototyping folder)
Feedback meeting booked for 31st March at 3.30pm
Technical focus more on front-end side than back-end
Useful Links
Purpose: | Link:

## 2303
Date: | 2021-03-23
Attendees: | All
Action Review
Action: | Progress:
Finalise prototype | Hamza | Finished
Share survey with friends and family | All | Finished
Create focus group of family and friends that we can keep talking to as our project develops | All | Ongoing
Become more familiar with the mean stack | All | Ongoing
New Actions and Owners
Action: | Owner: | Date of completion:
Everyone to complete their relevant workshop | all | next week
Decisions
Talked about timeline and what we need to be doing
Start report writing now
Technical development needs to be caught up
Useful Links
Purpose: | Link:

## 3103
Date: | 2021-03-23
Attendees: | All
Action Review
Action: | Progress:
Create focus group of family and friends that we can keep talking to as our project develops | All | Completed
Become more familiar with the mean stack | All | Completed
Everyone to complete their relevant workshop | all | Ongoing
New Actions and Owners
Action: | Owner: | Date of completion:
Start sprints | All | End of Easter
Decisions
Had feedback meeting with Allison and Marceli, discussed idea and potential for further development past literacy rates | Spoke about aspect of timeline and how the globe will light up as time continues
Have one person more responsible for write up of report, everyone contributes their own technical expertise then the writer will go over and finess the style | Wenda to help with front end if there are gaps that need filling and back end is not too demanding
Useful Links
Purpose: | Link: